## Slide 2: Con Edison’s Portfolio and Project Management Journey
Frank La Rocca
Director, Con Edison
Business Improvement Services
PC212

## Slide 3: My Objectives for Today
Share my experience in:
Establishing a governance framework for increased financial intelligence
Changing the culture and gaining "buy in" from top down
Building a credible Program Management Office (PMO)
Establishing a “Sweep” process to dynamically reallocate spend
Establishing baseline Metrics and delivering real bottom line savings
Gaining complete financial insight across a $2bn portfolio

## Slide 4: Corporate Landscape
Increased Cost Control
  Maintain our infrastructure/service at or below inflation
  Stabilize our rates
  Maximize our investments
Enhance External Relationships
  Enhance regulatory relationship

## Slide 5: My Background
22 years at KeySpan Energy (now National Grid)
  Entire career in Information Technology
  Final 7 years as CIO
5 years at Con Edison (2008)
  Capital Optimization
  Building an Enterprise Portfolio Management Office
  Governance
  Finance

## Slide 6: Where to start?
How much are we spending on projects/programs?
Are investments inline with the corporate strategy?
What is the strategic value of the portfolio?
Are we getting an appropriate return on investment?
What is an appropriate return on investment?
Are we utilizing our discretionary budget in the best way?
Do we have effective metrics to gauge our financial performance?

## Slide 7: Investment Optimization & Management
Optimization
The process of selecting the most strategic projects / programs and developing the optimal portfolio
Management
Focused on project execution, budget reinvestment, and measuring performance
Do the right projects AND Do projects right
Manage Portfolio
Select Projects
Propose Projects
Measure Portfolio
Promote Standardization through Defined Processes, Workflow, and Templates

## Slide 8: EPMO- Enterprise Program Management Office
Optimization
Management
Create
Select
Plan
Manage
Evaluate
Promote Standardization through Defined Processes, Workflow, and Templates
Standardize business case
Determine Strategic Value
High Level Cost/benefit Estimating
Contingency Estimating
Risk Impact
Strategic Alignment
Cost Optimizations
Resource Capacity Planning
Selected Portfolio
Schedule Mgmt.
Resource Assignments
Detailed Cost/benefit Estimating
Funding Approval
Variance/metric Reporting
Re-Investment “Sweep” Process
Scope & Schedule Delivery
Budget Utilization
Health Status Reporting
  Year-End Review
  Cost Benefits Realization Analysis
  Scope Realization Analysis
  Lessons Learned
$2bn – Process Managed by 2 Employees
$200m Pilot – 4 Employees
Expanding to $2bn

## Slide 9: Enterprise Program Management Office (EPMO)
Vision
To foster disciplined project management across Con Edison
maximizing our investments
ensuring strategic alignment
providing transparency
reducing execution risk
Increasing portfolio return on investment
providing coaching, mentorship and training to our project managers
and developing the supporting processes and technologies.

## Slide 10: Common Planning Challenges
Disparate methods of receiving project proposals
  Non standard business case
  Disparate financial models and calculations
  Disparate cost estimating methodologies
  Disparate method of linking benefit of strategic value
Disparate methods of classifying or categorizing project proposals
  Mandated
  Operationally Required
  Strategic
Often times projects are chosen based upon who submits and how fancy the “slide ware” is vs. the financial merit and strategic value
Small business units often lose
Impossible to compare financial value from one project to the next (apples to oranges)
Either cost over-runs or under-runs
Unable to distinguish between “lights on” and discretionary
Common Challenges
Typical Results
Propose Projects

## Slide 11: Capital Optimization: Methodology
To effectively compare the wide array of capital work that we do across our various business units we established a “strategic value currency”
  Enables us to quantifiably compare the benefit of doing one capital project or program over another
  Ensures that our spend is in alignment with our Corporate Strategy
Identified and prioritized our Strategic Drivers and formed several Governance Committees
Propose Projects

## Slide 12: Optimization Process and Governance Overview
Project
Assessment
Step 4:
Project
Prioritization
Step 5:
Portfolio
Analysis &
Constraint
Analysis
Step 6:
Impact
Statement
Definition
Step 3:
Driver
Definition
Step 1:
Final
Portfolio
Recommendation
Step 7:
Vice President Level
Senior Vice President Level
Driver
Prioritization
Step 2:

## Slide 13: Strategic Driver Definition
Driver Definition
Step 1:

## Slide 14: Strategic Driver Prioritization Results
Driver Prioritization
Step 2:

## Slide 15: Evaluating Projects Using Criteria
Project Assessment
Step 4:

## Slide 16: Analysis: Strategic Value & Cost
Project
Prioritization
Step 5:
High
Med
Low
Propose Projects

## Slide 17: Analysis: Applying Constraints
Portfolio Analysis &
Constraint Analysis
Step 6:
High
Med
Low
Constraint Analysis
Propose Projects

## Slide 18: Analysis: Evaluating Constraint Impact
Portfolio Analysis &
Constraint Analysis
Step 6:
Cost: $34 million
M
M
M
High
Med
Low
Constraint Analysis
Select Projects

## Slide 19: Aligning Our Spend with Our Vision
Portfolio Analysis &
Constraint Analysis
Step 6:
Select Projects

## Slide 20: Building Our Portfolios
Select Projects
Regulatory Mandated
Operationally Required
Strategic - with Cost Savings
Strategic - with Cost Avoidance
Strategic - Other
In Flight
Strategic Value

## Slide 21: Monthly Variance Reporting/Management
Manage Portfolio

## Slide 22
Chart: 
| Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
2013 Actual YTD Spend | 8.7715 | 15.1258 | 25.2894 | 39.2742 | 52.2001 | 65.6512 | 73.536 | 84.665 | 103.3772
2013 Projected YTD Spend | 79.6414 | 97.6939 | 121.5588 | 137.9 | 168.2 | 190.6
2011 & 2012 Average YTD Spend | 7.0951 | 14.6392 | 24.2146 | 34.9382 | 49.3249 | 66.4653 | 76.3765 | 89.1905 | 102.6452 | 117.9198 | 137.3681 | 172.5874
2013 Original Budget | 212
Qtr 1
revision
Qtr 2
revision
Qtr 3
revision
Variance Analysis
Manage Portfolio
Our September projections far exceed our historical spend patters
EPMO: Using trend analysis to better predict the future

## Slide 23: 2013- Portfolio Forecasting Accuracy – Spot On!
Measure Portfolio
Chart: 
| Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
2013 Actual YTD Spend | 8.7715 | 15.1258 | 25.2894 | 39.2742 | 52.2001 | 65.6512 | 73.536 | 85.66 | 103.3772 | 127.741 | 143.566 | 179.144
2011 & 2012 Average YTD Spend | 7.0951 | 14.6392 | 24.2146 | 34.9382 | 49.3249 | 66.4653 | 76.3765 | 89.1905 | 102.6452 | 117.9198 | 137.3681 | 172.5874
2013 Original Budget | 212
Comments
The Original Budget was $212M
Through the dynamic reallocation process we ‘gave back’ $33m
The YE Actual Charges were $179.1M, slightly above the 2 year trend, but very close to the November year-end projection of 179.6M

## Slide 24: EPMO: Budget and Utilization Trends
Measure Portfolio
Chart: Total Project Portfolio –Budget Utilization
| 2009 | 2010 | 2011 | 2012 | 2013
Original Budget | 244 | 211 | 180 | 188 | 212
Sanctioned Budget | 178
Actual Spend | 200 | 194 | 175 | 170 | 179
Original Budget Utilization % | 0.81967 | 0.91943 | 0.97222 | 0.90426 | 0.84434
Sanctioned Budget Utilization % | 1.0056
Our budget utilization rates have significantly increased over the years
In 2013, this portfolio “gave back” $33m, to the Corporation and came in at full budget utilization

## Slide 25: Portfolio Summary by Organization
Measure Portfolio
Organization | 2013 Requested | 2013 Approved | 2013 Actual Charges | 2013 Original Budget | Actual vs. Budget |  | November Forecast | Actual vs. Forecast | 
Organization 1 | $27,404 | $22,442 | $14,869 | $22,442 | ($7,574) | -34% | $15,991 | ($1,122) | -7%
Organization 2 | $73,851 | $62,864 | $50,236 | $62,864 | ($12,628) | -20% | $48,050 | $2,186 | 5%
Organization 3 | $0 | $0 | $197 | $0 | $197 | - | $195 | $2 | 1%
Organization 4 | $11,105 | $5,987 | $3,650 | $5,987 | ($2,337) | -39% | $3,683 | ($33) | -1%

## Slide 26: Developing Trends and Metrics
Measure Portfolio
Project Forecasting Accuracy
Avg. Deviation from Budget: 28%

## Slide 27: Project Forecasting Accuracy
Measure Portfolio
Organization | 2011 | 2012 | 2013
Information Resources | 18% | 19% | 12%
Facilities | 41% | 33% | 27%
Organization | 23% | 19% | 12%
Organization | 26% | 16% | 26%
Organization | 23% | 25% | 8%
Organization | 43% | 33% | 40%
Organization | - | 79% | 3%
Organization | 55% | 13% | 3%
Organization | 64% | 21% | 28%
Organization | - | 31% | 61%
Total | 38% | 27% | 26%

## Slide 28: EPMO: Learning Root Cause
Culturally, it is better to dramatically under-run than over-run slightly; generally leads to inflated cost estimates
Measure Portfolio
    Original cash flow do not reflect new/recent information
    Limited formal estimating or Project Management training
Often PMs did not create the original project estimate and felt “hostage” to the original “order of magnitude” estimate
The static nature of the annual planning process, thwarts their efforts
Limited formal estimating or Project Management training
No standard method of creating original estimates and no formal contingency estimating
Original cash flow does not reflect new/recent information
Feedback from Project Managers

## Slide 29: Dynamic Re-allocation in Action
23 new projects were funded due to timely releasing of funds; this traditionally would have been “left on the table”
“Not a spend it or lose it” mentality. Sweeps need to be strategic
Measure Portfolio
2012

## Slide 30: Dynamic Re-Allocation ‘Sweep’ Process
Manage Portfolio
Annual Budget Planning – Optimized Portfolio
EPMO: Monthly Summary Portfolio Report
Monthly
Dynamic Re-allocation Sanction Process
(Bi-monthly)
Senior Officer Committee
Organization X
Pre-Sanction meeting
EPMO, Cost Managers, and Project Managers
Monthly sanctioning process
  Releases – every month
  Re-directs – every month
  New – every month
  Re-forecasting – quarterly
Annual ‘proposal’ to selection and optimization budget process
Monthly Project Deep Dive:
  Project Status review
  Red, amber, green reporting
  Variance reporting
  Scope review
Governance review
Senior officer update
Organization Z
Pre-Sanction meeting
EPMO, Cost Managers, and Project Managers
Organization Y
Pre-Sanction meeting
EPMO, Cost Managers , and Project Managers

## Slide 31: Dynamic Re-Allocation ‘Sweep’ Process
Manage Portfolio
Releases
New Requests
Sanction Process
Re-directs
New
Revised SAC Sanctioned Budget
Any remaining funds not allocated to projects go back to the “pot” for next month’s strategic reinvestment
Releases always Approved
Re-Directs
Yes
No
Approved?

## Slide 32: New Projects Approved by Organization
Measure Portfolio
Organization | 2012 New Projects | % of Total
General Equipment | $5,430,000 | 31%
Customer Operations | $2,608,278 | 15%
Electric Ops | $2,500,000 | 14%
ESS | $2,391,040 | 14%
Finance | $1,743,491 | 10%
Central Operations | $1,192,000 | 7%
Facilities | $1,000,000 | 6%
Law | $605,000 | 3%
EH&S | $80,000 | 0%
Grand Total | $17,549,809 | 100%

## Slide 33: Redirects by Organization
Measure Portfolio
2012 Total Redirected: $15M
Organization | 2012 Redirect | % of Total
Facilities | $7,383,000 | 49%
Customer Operations | $3,579,000 | 24%
General Equipment | $1,500,000 | 10%
ESS | $1,327,501 | 9%
IR | $500,000 | 3%
Central Operations | $430,000 | 3%
Finance | $220,000 | 1%
Law | $78,000 | 1%
Grand Total | $15,017,501 | 100%

## Slide 34: Total Releases by Organization
Measure Portfolio
Organization | 2012 Release | % of Total
Facilities | $15,290,000 | 43.0%
Electric Ops | $6,500,000 | 18.3%
IR | $4,400,000 | 12.4%
Customer Operations | $3,274,000 | 9.2%
General Equipment | $2,345,000 | 6.6%
ESS (Energy Mgmt & HR ) | $1,935,260 | 5.4%
Central Operations | $973,000 | 2.7%
Finance | $850,000 | 2.4%
BSS (Central Field Services) |  | 0.0%
Law |  | 0.0%
EH&S |  | 0.0%
Grand Total | $35,567,260 | 100.0%

## Slide 35: Reasons for Releases by Organization
Measure Portfolio
Organization | Deferral Release - Planned scope could not be completed; will be deferred to next year | Forced Release- Due to Capital Budget Overruns | Permanent Release - Contingency Released | Permanent Release - Lower than Expected Costs | Permanent Release - Lower than Expected Vendor Costs | Permanent Release - Original Budget was created before project plan was solidified | Permanent Release - Permanent Credit Due to Adjustments (i.e., Overhead, Accrual Reversals) | Permanent Release - Scope Change | Grand Total
Information Resources (IR) | ($9,100,000) | ($1,250,000) |  |  |  |  | ($1,066) |  | ($10,351,066)
Central Field Services | ($1,500,168) |  |  |  |  |  |  |  | ($1,500,168)
Facilities | ($16,315,965) |  | ($348,000) | ($5,694,892) | ($1,447,730) |  |  | ($2,505,267) | ($26,311,854)
Organization | ($1,898,785) | ($254,000) | ($214,496) | ($26,235) |  |  | ($2,485) |  | ($2,396,001)
Organization |  | ($14,779,000) |  | ($500,000) |  |  |  |  | ($15,279,000)
Organization | ($385,853) | ($785,000) | ($70,000) | ($50,000) |  | ($588,044) |  | ($75,000) | ($1,953,897)
Organization |  | ($1,087,000) | ($607,000) | ($1,534,000) | ($1,515,930) | ($1,000,032) | ($19,553) | ($1,000,000) | ($6,763,515)
Organization | ($3,100,222) | ($780,000) |  |  |  |  |  |  | ($3,880,222)
Organization | ($4,340,649) | ($903,574) |  |  |  |  | ($1,205,090) |  | ($6,449,313)
Organization | ($1,203,000) | ($155,000) |  | ($75,000) |  |  |  |  | ($1,433,000)
Organization | ($28,000) | ($80,000) |  |  |  |  |  |  | ($108,000)
Grand Total | ($37,872,642) | ($20,073,574) | ($1,239,496) | ($7,880,127) | ($2,963,660) | ($1,588,076) | ($1,228,194) | ($3,580,267) | ($76,426,036)
Total Permanent Releases:
$18,524,306
Total Deferred Releases: $57,901,730

## Slide 36: EPMO: How to Measure Value
Prioritization/ Optimization
  Strategic Value
  Risk Reduction
  Cost Benefit
  Cost Avoidance
Execution – Calendar Year
Value assessment
Year-end metrics
  Budget utilization
  Estimating accuracy
  Forecasting accuracy
  Degree of churn
  Scope delivery
  Financial savings
Identify Continuous Improvement Opportunities
Annual Budget Planning
Post Year-End Review
  Strategy change
  Financial change
  Scope changes
  Resource changes
  Dynamic Re-allocation - sweep
Output
Input
CHURN
Measure Portfolio

## Slide 37: EPMO: Developing Trends and Metrics
Portfolio Churn Analysis
Reinvestment
Total Over spend
Total Under spend
Original Optimized Portfolio
Give Backs
Q1
Q2
Q3
Approved Increases
Over-Runs
New Projects
Under-Runs
Actual Portfolio =
Original Portfolio – Give Backs – Under-Runs + Approved Increases + Over-Runs + New Projects
% Portfolio Churn = 1- (Original Portfolio – Give Backs – Under-Runs) / Original Portfolio
$188M
$18
$9
$9
$14
$51M
27%
$15
$0
$15M
8%
$17.5M
9%
$17.5
Measure Portfolio

## Slide 38: EPMO: Developing Trends and Metrics
Reinvestment
Total Over spend
Total Under spend
Original Optimized Portfolio
Give Backs
Q1
Q2
Q3
Approved Increases
Over-Runs
New Projects
Under-Runs
Actual Portfolio = $170M
73% of Original Portfolio spent; 27% of Original Portfolio churned
$188M
$18
$9
$9
$14
$51M
27%
$15
$0
$15M
8%
$17.5M
9%
$17.5
Portfolio Churn Analysis
Measure Portfolio

## Slide 39: Building a credible EPMO
Where we were
Difficult to find a roster of all in-flight projects
Hard to track down the project managers
No formal tracking of start dates/end dates
No formal benefit estimating and limited follow up (except for large projects)
Limited project status reporting, no portfolio level reporting
No dynamic re-allocation process
No Project Management Society
No portfolio analytics/year-end reporting
  Budget utilization
  Estimating accuracy
  Delivered value
  Churn analysis
Silo’ d budgeting vs. shared budgeting
Informal project manager training
While it may be hard to measure the power of the PMO, each of these line items have increased the value we are getting from our portfolio

## Slide 40: Next Steps
Replicate what has been done with the $200m portfolio across the $2b portfolio further utilizing UMT360

## Slide 41
Get Stamped!
This was a UMT “Companies Delivering Big” session! See a UMT rep to get your booklet stamped.
Don’t know about the contest? Visit UMT @ booth 501 to learn more!

## Slide 42
Q&A
Deliver More ROI from Project Server.
laroccafr@coned.com

## Slide 43
MyPC fill out evaluations & win prizes!
Fill out session evaluations by logging
into MyPC on your laptop or mobile device.
Evaluation prizes daily! Claim your prize at the Registration Desk on Level 1.
www.msprojectconference.com
After the event, over 100 hours of resources; including all of the PPT decks and session videos will be available.

## Slide 44
© 2014 Microsoft Corporation. All rights reserved. Microsoft, Windows and other product names are or may be registered trademarks and/or trademarks in the U.S. and/or other countries.
The information herein is for informational purposes only and represents the current view of Microsoft Corporation as of the date of this presentation. Because Microsoft must respond to changing market conditions, it should not be interpreted to be a commitment on the part of Microsoft, and Microsoft cannot guarantee the accuracy of any information provided after the date of this presentation. MICROSOFT MAKES NO WARRANTIES, EXPRESS, IMPLIED OR STATUTORY, AS TO THE INFORMATION IN THIS PRESENTATION.