## Slide 2: Monitoring the PMO
Michael Wharton, MVP
Project/SharePoint Architect
Wharton Computer Consulting
PC276

## Slide 3: Speaker: Michael Wharton
Awarded Project MVP (Microsoft Valuable Professional)
Ten Years Experience with Project Pro and Project Server
Over 25 Project Server Deployments into PMO
Over seven Project Server Migrations
Passed over 42 Microsoft Certification Exams
Trained over thousand Project Managers with Project Professional
Technical Reviewer for Missing Manual: Project Professional 2013 by Biafore
Contributor to: Project Management Using MS Project 2013 by Cicala
Web Site: www.WhartonComputer.Com
Blog: www.MyProjectExpert.com
Twitter: MyProjectExpert
Notes: Key Point: That’s’ me.. I have been in project server space for 10 years and have worked with a lot of great people and companies.
Have meet a lot of great project managers and learned a lot.
They great thing about working with different companies, is that I learn about what is working and not working.
Gaining a lot of experience.. And the truth is that you can’t google experience.
Its been a great ride!

## Slide 4: MONITOR PMO
Notes: Key Point: Only TWO WORDS that I want you to remember when you leave today MONITOR PMO

## Slide 5: Agenda
PMO Monitoring Overview
Monitoring Road Map
Identifying Key PMO Governance Metrics
Monitoring Tools and Methods
Using Dashboard to Monitor PMO Trends
Deep Dive into Monitoring
Project and Resource Conformance Index
Putting It All Together
Notes: 1. Identifying key PMO cycles that require monitoring and deadline times
2. Identifying key Conformance Indexes of Project Schedule
3. Identifying Key Conformance fields of Resource
4. Identifying Key Conformance field of Task
5. Building SQL Queries
6. Tools for monitoring
7. Monitoring Project Server health

## Slide 6: Who Are You?
Notes: Show of hands:
How many PMO Professionals?
How many IT Professionals?
How many have issues with current data?
How many have issues with PWA data?
How many have issues making sure timesheets and task sheets being submitted on time?
How many currently monitor PMO?

## Slide 7: PMO Monitoring Overview

## Slide 8: My History of PMO Monitoring
PMO Sheriff
Communicating the PMO Message
Getting People Involve and Engaged
Verifying that PMO Cycles are happening
Synchronizing User Roles and Processes
One-on-one coaching with PM, RM and Team
Notes: Key Point: Fortunate to be able to be on site with several large PMO and working one-on-one with project managers and PMO
Key Points: PMO Enforcer -- not at first
Was there to help coaching Project Managers and Resource Manager
Many of there problems started stemming from cycles not occurring, timesheets not submitted, status dates not being update,
Started looking for ways to find out what was happening across the PMO
but started to become
Key Point: Communicating the PMO message and why its so important
Each PMO has different requirements
Each PMO has different processes
New PMOs and Existing PMOs have same issues
Getting Roles and Processes synchronized
PMO needs one-on-one coaching with PM and RM
Auditing of procedures

## Slide 9: PMBOK Definition of Monitoring
Regular measures and monitors progress to identify variances from the project management plan so that corrective action can be taken when necessary to meet project objectives.
Monitoring and Controlling
Processes
Initiating Processes
Closing Processes
Planning Processes
Executing Processes
Notes: Key Points: Fundamentals of PMI Process Groups and Monitoring is one of them
Key Point: Monitoring and Controlling Process Group: Regular measures and monitors progress to identify variances from the project management plan so that corrective action can be taken when necessary to meet project objectives.
PMO Monitoring based on PMBOK
Project Manager Monitors Project
Scope: This session is not about monitoring a project. For example, monitoring costs or schedules, excel reports that a specific to a project.

## Slide 10: Definition of PMO Monitoring
PMO Monitoring, Notifying and Trends
Regular measures and monitors PMO standards, process cycles and meta data so that corrective action can be taken when necessary to meet PMO governance objectives.
Monitoring & Controlling Processes
Initiating Processes
Closing Processes
Planning Processes
Executing Processes
Gate 2
Gate 3
Security
Roles
Resource
Profiles & Capacity
PMO Governance
Notes: Key Points: Regular measures and monitors PMO standards, process cycles and meta data so that corrective action can be taken when necessary to meet PMO governance objectives.
PMO Manager manages all projects, resource, phases, etc
PMO manages and monitors all the projects and resources,
Key Point: Monitoring and Controlling PMO: Regular measures and monitors all projects and resources in the PMO to insure that
data is correct and current,
all process in PMO are being followed,
By prompting all roles and resources to do PMO updates as required
Key Point: Monitoring and Controlling Process Group: Regular measures and monitors progress to identify variances from the project management plan so that corrective action can be taken when necessary to meet project objectives

## Slide 11: New Sheriff is in PMO
Execution of all PMO cycles
Ensuring Accurate and Timely Data
Ensure Standards and Governance are Meet
Prompting Others TO DO
Creating good habits
Notes: Key Point: New Sheriff… we don’t use bullets or hand cuffs--- we use email and text message
Need to Follow Standards and Governance
Need to Follow Common Procedures
Need to Manage PMO cycles
Need for Ensuring Accurate and Timely Data
Need for Efficiency and Automation
Need for Synchronization

## Slide 12: Monitoring Road Map

## Slide 13: Steps to Build Monitoring and Automation
Identify Key PMO Governance Metrics
Implement Basic Manual Monitoring
Build Automated Processes for Notification
Build Dashboards for Trending
Back to Top
Notes: Key Points: Steps to Build Monitoring and Automation
Identify Key PMO Governance Metrics
Implement Manual Monitoring
Build Processes for Automation and Notification
Build Dashboards
Go Back to step one

## Slide 14: Identify Key PMO Governance Metrics

## Slide 15: Key PMO Standards
Project Schedule Standards and Metadata
Project Work Space and Documents
Historical Snapshot of Project Status
Project Schedule Conformance Index
Resource Profile Data
Vacation Summary
Historical Snapshot of Resource Profile
Security Roles
Timesheets and Task sheets
Approval of Status Updates
Approvals of Timesheets
Updating Project Status Date
Regular Publishing of Schedules
Resource Workflows
Project Standards
Resource Standards
PMO Project and Resource Cycles
Notes: Key Points: Identify Key PMO Governance Metrics
Project Data
Project Schedule standards
Project Gates
Summary Tasks
Milestones
Milestones(key project metrics, do tasks have GATES that ne
Project Meta Data (missing data as project move through different phases of project)
Project Workspace Data ( missing documents, signatures, review)
Risk and Issues (
Resource Data
Resource Profile Data (missing data, last login)
Managing Resource Workflow (new resources on board, resources that left the company)
Resource over allocated
PMO Cycles
Timesheets and Task Sheets (submitting and remaindering users to submit timesheet)
Approvals and Project Status (checking that time has been approved, checking that project status )
Publishing Projects (publishing updated projects)
Managing Project Workflows (managing other workflows in project)
Project Schedule Conformance Index
Providing an index of is included in project schedule

## Slide 16: Basic Manual Monitoring Example

## Slide 17: Simple and Manual Monitoring Tools
Weekly Check List
Out-of-box PWA Views and Custom Views
  Resource Center
  Project Center
  Server Setting / Manage Users
Delegation
  Timesheet Examination as Resource
  Approval History as Timesheet Manager
  Project Schedule Review of Project Manager
Excel Spreadsheet Reports
  Excel Spread Sheets
  BI and Dashboards
Notes: Key Point: Simple and Manual means, that someone has to do this
Key Point: Creating a check list each week and reviewing data
Out-of-box PWA Views and Custom Views
  Resource Center
  Project Center
  Server Setting / Manage Users
Delegation
  Timesheet Examination as Resource
  Approval History as Timesheet Manager
  Project Schedule Review of Project Manager
Excel Spread Sheets
  Excel Spread Sheets
  BI and Dashboards

## Slide 18: First Step for PMO Monitoring
Notes: Jumping Straight into Monitoring with a simple example
Key Point: “Last Connect” is best first step tool for monitoring PMO
Simple First Step: Server Settings / Manage Users
Lots of information can be derived from this single view and get you going
Key Point: I may EXPORT to EXCEL and do more filtering
Blank “Last Connect” Date
Last connect older than 1 week
Last connect older than 2 weeks
Blank “Last Connect” Date
User not using PWA
User has not accessed PWA
User unaware of using PWA
User needs Training
User access denied
Invalid user account
Duplicate accounts
Action – PMO needs to reach out to user
Resolve connection Issue
Direct to training materials
One-on-one coaching
Last connect older than 1 week
User is on vacation
User not in habit of using PWA
User has forgotten to enter time
User has left the company
Action – Find out why and Resolve
User is on vacation: OK
User not in habit of using PWA: Put a reminder in Outlook
User has forgotten to enter time: Send reminder
User has left the company: Inactivate user
Last connect older than 2 weeks
Project Manager not using tool
Resource Manager not using tool
Management not using tool
Action – Find out why and Resolve
Additional Training
One-on-one coaching
Additional Automation

## Slide 19: Any View can be Created using SQL
Notes: Key Point: Enterprise Resource Fields
Flags to Exclude (all) - Service Accounts
Flags to ExcludeManagers
Flag to identify PILOT or NEW ROLL
Key Point: Existing Resource Flag
Earliest Available
Latest Available

## Slide 20: Spreadsheet with many Monitoring tabs
Notes: Other tabs
Mismatch of Project Managers and Status Managers
Tasked with Missed Deadlines
“Status Date” not current in project schedule
Tasks with zero actual work starting in the past

## Slide 21: A few other monitor tabs
Mismatch of Project Managers and Status Managers
Tasked with Missed Deadlines
“Status Date” not current in project schedule
Tasks starting in the past
Resources assigned to Milestones or Summaries
Resources Defined as Self Approving
Resources without any Task assignments
Notes: Mismatch of Project Managers and Status Managers
Tasked with Missed Deadlines
“Status Date” not current in project schedule
Tasks starting in the past
Back to the important of Status
Timesheets line with more work than remaining work
Issues processing timesheets
Resources assigned to Milestones or Summaries
Resources Defined as Self Approving
Resources without any Task assignments

## Slide 22: Automated Tools and Methods

## Slide 23: Automation and Notifications
Friday broadcast to submit time and status
Monday Morning Reminders – email or text
Embarrassing Reminders – send to all
Stressful Reminders -- send to manager
Monday Afternoon Reminders with CC: PMO staff
Tuesday Morning Reminders with CC: Managers
Notes: Windows Scheduler
Can be used to kick off jobs for
SQL Server Agent
Can be use to kick of jobs
SSRS (SQL Server Reporting Services)
  Subscriptions - General Report History
  Snapshots of Projects, Resources and Other Status as Excel Reports
  General Email Notification
  PMO Reporting
SSIS (SQL Server Integration Services)
  Intelligent steps to manage monitoring – building emails that hit specific targets, users and resource managers
  Individual Notification for missing data

## Slide 24: Tools to Automate Monitoring
Windows Scheduler
SQL Server Agent
SSRS (SQL Server Reporting Services)
SSIS (SQL Server Integration Services)
Notes: Windows Scheduler
Can be used to kick off jobs for
SQL Server Agent
Can be use to kick of jobs
SSRS (SQL Server Reporting Services)
  Subscriptions - General Report History
  Snapshots of Projects, Resources and Other Status as Excel Reports
  General Email Notification
  PMO Reporting
SSIS (SQL Server Integration Services)
  Intelligent steps to manage monitoring – building emails that hit specific targets, users and resource managers
  Individual Notification for missing data

## Slide 25: Dashboard Trends

## Slide 26: Dashboard PMO Trends
PMO Growth Trends
Cycle Processing Trends
Projects Trends
Resource Trends
Notes: Key Point: Dashboard to show trends
Growth of PMO Membership: Weekly or monthly count of users
Growth of Projects in PMO: Weekly or monthly count
Growth of Resource in PMO: Weekly or monthly
Membership Growth
  Team Members
  Project Managers
  Resource Managers
  Executive Managers log in
Processing Trends
  Missing Timesheets
  Status Updates
  Timesheets Submitted
  Hours Recorded over Time
  Document in Project workspace

## Slide 27: PMO Growth Dashboard
Notes: Key Point: PMO Director or Executive View showing how well PMO Growth
Key Point: Encouraging to see growth and shows that the rollout is happening.
Resource Usage Growth:
Pilot, then slow rollout to more
All phases of deployment can start using PMO
Based on Resource Count or Last Login Count
PMO Reach
Looking at total number of Employees and how many are using Project Server

## Slide 28: PMO Cycles Dashboard
Notes: Key Point:
Project Growth and PM
Timesheet Reminder
Project Status
Project Publishing

## Slide 29: PMO Projects Dashboard
Notes: Key Point: Projects Dashboards - Some of the metrics will be found in the PMO Cycle Dashboard
Project Phase Gate Counts
Schedule Conformance Index

## Slide 30: PMO Resource Dashboard
Notes: Key Point: Resource Dashboards
Unapproved Timesheets
Resource Managers vs Resource
Number of Resources Over allocated by more than 100%
Number of Resource Under Utilized… Less than 50%
Vacation Time Required
New Resources vs Inactive Resources
Resource Growth vs No Login
Resource Growth vs Missing Timesheet

## Slide 31: Deep Dive Ideas for PMO Monitoring

## Slide 32: Basic Project Update Cycle
2. Check Missing Timesheets
and Task sheets
4. Check Project Status Approvals
6. Check Status Dates and Published
1. Resource Submits Time
5. Project Manager Updates Schedule and Publish
3. Project Manager Approvals
Notes: Key Concept: Critical that weekly events are occurring and reminders are sent
Key Concept: Monitoring should be done as during deployment
Missing Timesheets and Task Sheets from Resources
Reminders to resource to submit times
Reminders that 40 hours is submit for full time
  Using Delegation
  SQL Query to send notification
Missing Status Approvals from Project Managers
Reminder to project managers to approve status
  Using Delegation you can look into from View
  SQL query to send notification
Missing Timesheets Approvals
Reminder to Resource Manages to approve timesheets
  Using Delegation you can look into
  SQL Query to send notification
Updating of Project Status
Reminders to Project Managers to update project schedule and status dates (not a view that shows this)
  Write SQL Query to send notifications
Publishing Projects after Updates
Reminder to Project Managers to publish schedules (Project Center view can show last published)
  Write SQL Query to send notifications
  List of Who Has Timesheet in Progress
  List of Submitted Timesheet
  Project Manager Approved Status Updates
  Resource Manager Approved Timesheet

## Slide 33: Email Reminders
Check Missing Timesheets
and Task sheets
Check Project Status and Timesheet Approvals
Check Status Dates and Published
Monday noon
Tuesday noon
Wednesday noon
Notes: Key Concept: Critical that weekly events are occurring and reminders are sent
Key Concept: Monitoring should be done as during deployment
Missing Timesheets and Task Sheets from Resources
Reminders to resource to submit times
Reminders that 40 hours is submit for full time
  Using Delegation
  SQL Query to send notification
Missing Status Approvals from Project Managers
Reminder to project managers to approve status
  Using Delegation you can look into from View
  SQL query to send notification
Missing Timesheets Approvals
Reminder to Resource Manages to approve timesheets
  Using Delegation you can look into
  SQL Query to send notification
Updating of Project Status
Reminders to Project Managers to update project schedule and status dates (not a view that shows this)
  Write SQL Query to send notifications
Publishing Projects after Updates
Reminder to Project Managers to publish schedules (Project Center view can show last published)
  Write SQL Query to send notifications
  List of Who Has Timesheet in Progress
  List of Submitted Timesheet
  Project Manager Approved Status Updates
  Resource Manager Approved Timesheet

## Slide 34: Monitoring Approval Cycle
Notes: Key Concept: Monitoring Approval Cycle – This could be in your PMO Monitor Spread sheet
Timesheet must be submitted and Received by Noon Monday
Status Updates must be approved and projects updated by Tuesday Noon
Timesheet must be approved by Tuesday Noon ---
Schedules must be published by Noon Wednesday

## Slide 35: Monitoring Project Metadata
Missing Data
Baselines Not Set
Deadlines Missed
Project Manager and Status Manager mismatch
Missing Documents in Workspace
Email Summary Reports to PMO and Exec
Notes: Key Points:
Missing Data in Project Detail Pages
Data: Missing sponsor, project manager, security person, costs estimates, propose dates, etc
Manual: Project View with that is inspected
Automation: SQL query to find missing data and send email to project manager
Missing Data moving thru Gate Gates
Manual: Project View with that is inspected
Automation: SQL query to find missing data and send email to project manager
Email alerts on missed deadlines
Manual: SQL query to find missed deadlines
Automation: SQL query to find missed deadlines and send email to project manager
Missing Document in Workspace
Manual: Project View with that is inspected
Automation: SQL query to find missing data and send email to project manager
Unsigned Documents in Workspaces
Manual: Project View with that is inspected
Automation: SQL query to find missing data and send email to project manager

## Slide 36: Create Views to Show Missing Data
Notes: Key Point: Create View so to find missing data in Project
Use Filters to
Use Group
Sort by
Key Point: Any view can be created with SQL statement and put into Excel Sheet
Send Project Manager details of what is missing
Add Slide with view of missing data in Project Center
Metrics of Number of Projects
Metric of Missing Data count

## Slide 37: Historical Snapshot of Project Data
Project Summary of Hours and Cost
Project Summary By Gate by Week
Project Summary By Resource By Week
Project Details by Week
Notes: Key Points: Have you ever wonder what the project cost or work effort was for a project a few months ago. Not going to find it easy
Key Points: Snapshot for Historical Data
There is no historical data in project server ---- you must create some of it
Put into a Spreadsheet…. Even better is to push into another database
Key Point: SSRS to automate snapshots
Key Point SSIS to push into databases – easier to find using queries

## Slide 38: Monitoring Resource MetaData
Missing data in Resource Profile
Resource Profile not properly defined
  Employees setup as Self Approve
  RBS incorrect
  Timesheet manager
  Resource Flags not set
Resources in correct Security Groups
New Employees not Logged in
Terminated Employees not set inactive
Email Upcoming Resource Vacations
Notes: Monitoring Resource Metadata
Key Concepts
Missing data in Resource Profile ( key profile data missing)
Resource Profile not properly defined (verify profile data correct)
Employees setup as Self Approve
RBS incorrect
Timesheet manager
Resource Flags not set
New Employees not Logged in (do they need training or awareness)
Terminated Employees not set inactive (

## Slide 39: Resource Profile Missing Data
Notes: Key Point: Keeping the Resource Profile fresh and update to date
Key Point: Checking for missing resource metadata
Key Point: SQL query and results sent to project manager would be much better
Resource Center: View with
Position Role: Missing data
Email Address: Missing data
Notice: With Timesheet Manager, a SQL query could be put into spread or automated process to send email to verify.

## Slide 40: Historical Snapshot of Resource Data
Resource Summary of Hours and Cost
Resource Summary By Project By Week
Resource Summary By Week For Day-2-Day
Resource Task Details by Week
Resource Vacation Actual Hours YTD
Notes: Key Point: Has someone deleted their timesheet by accident and you need what they entered, a few weeks ago or months ago
Key Points: Snapshot for Historical Data
There is no historical data in project server ---- you must create some of it
Put into a Spreadsheet…. Even better is to push into another database
Key Point: SSRS to automate snapshots
Key Point SSIS to push into databases – easier to find using queries

## Slide 41: Project Schedule and Resource Conformance Index

## Slide 42: Project Schedule Conformance Index (PSCI)
Provides Index for Project Schedules
Conformance Index based on your Governance
PSCI Example
  Missing Phases and Milestones
  Milestones Missing Deadlines Dates
  Unassigned Resources
  Unassigned Task
  Too Few Task vs Too Detail Tasks
  Missing Task Attributes (Capital / Expense)
  Missing Baseline
Notes: Degree of compliance of a schedule within PMO
Key Point: PMI Scheduling Certification and has a Conformance Index for Schedules
Provides Index for Standard Schedules
Project Conformance Index Based on PMO Governance
  Rules
  Weight
Example
  Missing Standard Phases and Milestones
  Unassigned Resources
  Unassigned Task
  Too Few Task
  Too Detail Tasks
  Status Date off by two week

## Slide 43: Designing a PSCI
Made up of scheduling best practices
Minus point for bad practices
Plus points for good practices
Score between 0 to 100 for each project
PM receives audit report with explanation
Notes: Key Point: Conformance Index of Project Schedule
Loosely based on PMI “Conformance Index” from the Practice Standard for Scheduling
However Concept can be integrated in the PMO Monitoring in that we want project schedule to have minimum conformance to be effective
Degree of compliance of a schedule within PMO
Made up of scheduling best practices
Plus points for good practices
Dynamic schedule
Using As Soon As Possible
Scheduling Forward
Task with duration not less than 1 day
Phase gates in the schedule
All Task types are defined.
Minus point for bad practices
Assigning resources to summary task
Assigning more than 7 resources to a task
To Few Task
To Many task
No baseline
Score is created between 0 to 100

## Slide 44: Sample Metrics for PSCI
Notes: Key Concept: 50 / 64 * 100 Weighted Score / Score
Build Project Schedule Conformance Index in Excel
Translate to SQL query
Automate for Index and reports to project manager

## Slide 45: Project Schedule Conformance Index
Chart: Project Meeting PSCI Standard
| Jan | Feb | March | April | May | June
Meets Standard | 24 | 31 | 36 | 39 | 43 | 56
Needs Improvement | 56 | 50 | 46 | 49 | 40 | 32
Below Standard | 45 | 34 | 33 | 30 | 20 | 15
Notes: Key Point: Number of Project Schedules meeting Conformance Index standard over time
Green: Positive and showing the number of good project schedules
Yellow: Positive .. Needing improvement.. Need training
Red: Not meeting the project schedule standard.. New Project Manager and need for training

## Slide 46: Resource Conformance Index
Degree of compliance of a resource load within PMO
Made up of resource management best practices
Plus points for good practices
Minus point for bad practices
Score created between 0 to 100 for each Resource
Resource Manager receives audit report
Notes: Key Point: Conformance Index of Project Schedule
Loosely based on PMI “Conformance Index” from the Practice Standard for Scheduling
However Concept can be integrated in the PMO Monitoring in that we want project schedule to have minimum conformance to be effective
Degree of compliance of a schedule within PMO
Made up of scheduling best practices
Plus points for good practices
Dynamic schedule
Using As Soon As Possible
Scheduling Forward
Task with duration not less than 1 day
Phase gates in the schedule
All Task types are defined.
Minus point for bad practices
Assigning resources to summary task
Assigning more than 7 resources to a task
To Few Task
To Many task
No baseline
Score is created between 0 to 100

## Slide 47: Resource Conformance Index
Notes: Key Concept
Build Project Schedule Conformance Index in Excel
Translate to SQL query
Automate for Index and reports to project manager

## Slide 48: Resource Conformance Index
Chart: Resource Conformance Index
| Jan | Feb | March | April | May | June
Meets Standard | 56 | 62 | 65 | 69 | 72 | 77
Needs Improvement | 24 | 18 | 19 | 12 | 8 | 4
Notes: Key Point: Number of Project Schedules meeting Conformance Index standard over time
Green: Positive and showing the number of good project schedules
Yellow: Positive .. Needing improvement.. Need training
Red: Not meeting the project schedule standard.. New Project Manager and need for training

## Slide 49: Putting it All Together

## Slide 50: Putting it All Together
Identify Big Monitoring Hits
Start with Manual Monitoring
Build Automated Processes for Notification
Build Dashboard for Trends
Back To Top
Notes: Identify Big Monitoring Hits
Pain Points
Missing Data
Reminders
Implement Manual Monitoring
Out of box Views
Excel Spreadsheets
Dashboards
Build Automated Processes for Notification / Habits and Reminders
Windows
SQL Agent
SSRS
SSIS
Build Dashboard for Trends
Watch for trends
Back To Top

## Slide 51: When to Start PMO Monitoring?
Notes: Key Point: Monitoring can start NOW
Some organization spend way too much planning and preparing for deployment
Others a week or two of planning an jump in
In both cases, there is abruption that happens during implementation
And it’s monitoring

## Slide 52: Questions and Comments

## Slide 53: For More Information on PMO Monitoring
MyProjectExpert.com (Blog)
WhartonComputer.com
mwharton@whartoncomputer.com

## Slide 54: Thank You!

## Slide 55
MyPC fill out evaluations & win prizes!
Fill out session evaluations by logging
into MyPC on your laptop or mobile device.
Evaluation prizes daily! Claim your prize at the Registration Desk on Level 1.
www.msprojectconference.com
After the event, over 100 hours of resources; including all of the PPT decks and session videos will be available.

## Slide 56
© 2014 Microsoft Corporation. All rights reserved. Microsoft, Windows and other product names are or may be registered trademarks and/or trademarks in the U.S. and/or other countries.
The information herein is for informational purposes only and represents the current view of Microsoft Corporation as of the date of this presentation. Because Microsoft must respond to changing market conditions, it should not be interpreted to be a commitment on the part of Microsoft, and Microsoft cannot guarantee the accuracy of any information provided after the date of this presentation. MICROSOFT MAKES NO WARRANTIES, EXPRESS, IMPLIED OR STATUTORY, AS TO THE INFORMATION IN THIS PRESENTATION.

## Slide 57: PMO Project Monitoring
Notes: Key Point: Dashboards can be used to enhance progress over time
Note: Build a better dashbaord
Add Slide with view of missing data in Project Center
Metrics of Number of Projects
Metric of Missing Data count

## Slide 58: Backend Monitoring
Project Server Database Integrity
  Finding Orphan Records
  Miscellaneous Data integrity
SharePoint Growth
  Content Database Growth
  Project Server Database
  SharePoint Monitoring
SQL Database Maintenance
  Disk Space
  Reindexing
  Backups